DataSol_Gateway

# driver_mssql - SQL Server driver proposal

Version 1.1

2026-10-24  (supersedes v1.0, 2026-10-18)

About this version (v1.1, 2026-10-24) Stages 1-7 have been built. This version adds Section 9, As built: what each stage delivered and how it was proven (9.1), every place the build differs from this proposal and why (9.2), the rule for procedures that commit (9.3), the deployment prerequisites (9.4), the tester on SQL Server (9.5), known differences and open items (9.6), and the status against the Definition of done (9.7). Sections 1-8 are kept as agreed on 18 Oct, so the original reasoning stays readable. The Section 3 states are brought up to date, and M8 is marked where the build went another way. Where Sections 1-8 and Section 9 differ, Section 9 holds. v1.0 (2026-10-18): first version - design points M1-M11 and decisions D1-D10, all agreed 18 Oct.

# 1. Purpose and scope

The Oracle dialect extraction (stages 0-6, closed 10 Oct) moved every Oracle call behind db_driver_t (20 hooks) and every piece of Oracle SQL text behind db_dialect_t (9 hooks). M2 (17 Oct) removed the last Oracle types from the shared context. Core code now compiles with Oracle's headers blocked, so a second driver can be added without touching core logic.

This proposal adds driver_mssql, a SQL Server driver written against ODBC. Oracle stays the default and must keep 13/13 harnesses and 109/109 in the HTTP tester at every stage.

In scope: connecting and pooling, SELECT (scalars and LOBs), INSERT/UPDATE/DELETE with LOB writes, transactions, stored procedures with result sets, table metadata, the SQL Server test database and its reset script, driver harnesses, and a SQL Server run of the HTTP tester.

Out of scope (M8): the DDL module; Unit_Test_Module's own verification queries; making SELECT output formatting (dates, numbers) identical on both databases; renaming oci_context_t.

# 2. Starting point

| Item | State |
| --- | --- |
| Driver interface | db_driver.h: db_driver_t - connect, disconnect, get_session, release_session, session_is_alive, reconnect_session, health_check, select_open, select_fetch_batch, select_close, dml_execute, commit, rollback, dml_execute_returning_rowids, rowid_result_free, lob_write_by_rowid, dml_execute_procedure, select_open_from_cursor, describe_table, cursor_handle_free - plus dialect. |
| Dialect | db_dialect_t: bind_placeholder, value_expr, lob_placeholder, row_locator_clauses, row_limit_sql, count_rows_sql, now_expr, add_seconds_expr, procedure_call_sql. The header comments already name the SQL Server forms. |
| Dispatch | db_driver_get() in db_driver.c always returns oracle_driver_get(). This is the one place that changes to choose a driver. |
| Shared context | M2 closed 17 Oct: the handle fields of oci_context_t are void *; lob_item_t uses standard types. Proof: m2_compile_proof.py PASS. |
| Shared helpers | lob_output_tag(), the LOB file naming and .part write (Blob_Utils.c / Clob_Utils.c), date_normalize, db_type_class.c and the resultset builder are core, so driver_mssql reuses them. |
| SQL Server | SQL Server 2022 CU27-GDR (16.0.4305.5), Developer Edition, Docker container mssql2022, port 1433, volume mssql2022_data. Client: ODBC Driver 18 for SQL Server 18.7.1.1, unixODBC 2.3.12, sqlcmd. Checked from the laptop with SELECT @@VERSION. |

# 3. Design points

| Point | Subject | State |
| --- | --- | --- |
| M1 | ODBC Driver 18 through unixODBC, ODBC 3.8 API | Done (Stage 2) |
| M2 | Vendor-neutral shared context | Done 17 Oct |
| M3 | db_type, mssql_* config keys, driver's own slot pool | Done (Stage 2; keys differ - 9.2) |
| M4 | Transactions: autocommit off, SQLEndTran, no retryable commit | Done (Stages 2, 4, 6; see 9.3) |
| M5 | Dialect: the nine SQL fragments | Done (Stages 3-4; 9.2) |
| M6 | Fetching, metadata, type classes, procedures | Done (Stages 3, 5, 6; 9.2) |
| M7 | Error text | Done (Stage 2) |
| M8 | Out of scope | Agreed; DDL not refused (9.2) |
| M9 | Build | Done (9.2 names) |
| M10 | Test database scripts | Done (Stage 1) |
| M11 | Stages and proof | Stages 1-6 closed; 7 in proof (9.7) |

## M1. ODBC Driver 18 through unixODBC

driver_mssql talks to SQL Server through the ODBC 3.8 API (SQL_OV_ODBC3_80), using Microsoft's ODBC Driver 18 for SQL Server, loaded by unixODBC. This is Microsoft's supported client on Linux, and it is already installed and tested on the laptop.

- Handles. One SQLHENV per process; one SQLHDBC per pool slot; a SQLHSTMT per operation. In oci_context_t, envhp holds the SQLHENV and svchp the SQLHDBC. errhp, srvhp and authp stay NULL: ODBC reports errors on the handle that failed, so there is no separate error handle. Core never looks inside these fields (M2).

- ODBC's own connection pooling is off. The gateway already pools sessions (M3); two pools would hide connection loss from session_is_alive.

- Connection string: Driver={ODBC Driver 18 for SQL Server};Server=tcp:<host>,<port>;Database=<db>;UID=<user>;PWD=<password>;Encrypt=yes;TrustServerCertificate=<yes|no>;APP=DataSol_Gateway. The password is never logged; the logged form shows PWD=***.

- Encryption. Driver 18 encrypts by default. The test container has a self-signed certificate, so the test config sets TrustServerCertificate=yes. A real server should present a trusted certificate and use no.

## M2. Vendor-neutral context - done 17 Oct

Connection.h no longer includes <oci.h>; the five handles are void *; lob_item_t uses uint32_t and void *; the two core uses of Oracle scalar types were made standard. 15 Oracle-side files include <oci.h> themselves. Proof: m2_compile_proof.py (56 core files compile with every Oracle header blocked; 19 Oracle-side files compile against the real headers with -Werror=incompatible-pointer-types), 13/13, tester 109/109. It becomes Grep 3 of the Definition of done (Section 7), and M9 extends it to the SQL Server files.

## M3. Choosing the driver, configuration and pool

- db_type = oracle | mssql in config.ini. Absent means oracle, so existing configs behave exactly as today. An unknown value stops the gateway at startup with a clear message.

- Dispatch. db_driver_get() returns mssql_driver_get() or oracle_driver_get() from the ini value read at startup. Every caller already goes through it, so nothing else changes.

- New keys (D1): mssql_server, mssql_port (default 1433), mssql_database, mssql_user, mssql_password, mssql_trust_server_certificate (default 0), mssql_login_timeout (default 15 s). The password is held and protected the same way as the Oracle password today. The existing pool keys (use_connection_pool, pool sizes, query timeout, fetch sizes) apply to both drivers.

- Pool. driver_mssql keeps its own slot pool with the same contract as Connection_Pool.c: get_session lends a connected slot, release_session returns it, session_is_alive checks SQL_ATTR_CONNECTION_DEAD (no round trip), reconnect_session replaces a dead connection, and health_check runs SELECT 1. A slot is rolled back before it is lent again, so no work leaks between requests.

- Login. The gateway connects as its own DATA_MANAGER login, never sa. The sa password stays out of config files, scripts and project documents.

## M4. Transactions

- Autocommit off on every connection (SQL_ATTR_AUTOCOMMIT = SQL_AUTOCOMMIT_OFF), matching Oracle, where nothing is committed until commit is called.

- commit and rollback call SQLEndTran(SQL_HANDLE_DBC, ...) on the session's connection.

- No retryable commit failures (D2). driver_mssql never returns DB_TX_RETRYABLE. A deadlock (error 1205) makes SQL Server roll back the whole transaction, so retrying only the commit would wrongly report success for work that was undone. A lost connection (SQLSTATE 08S01) leaves the outcome unknown. Both fail at once, with the error text from M7.

- Read consistency (D3): the test database runs with READ_COMMITTED_SNAPSHOT ON. Readers then see the last committed version of a row instead of waiting for writers, as on Oracle. Without it, the tester's 8 threads would block each other's SELECTs on uncommitted inserts and updates.

- Query timeout: the request's query_timeout is set with SQL_ATTR_QUERY_TIMEOUT on each statement.

## M5. Dialect

Each db_dialect_t hook, with the text driver_oracle produces today and the text driver_mssql will produce:

| Hook | Oracle | SQL Server |
| --- | --- | --- |
| bind_placeholder | :5 | ? (ODBC binds by position) |
| value_expr | TO_DATE(:3,'YYYY-MM-DD HH24:MI:SS') for DATE; operand unchanged otherwise | CAST(? AS datetime2(7)) for datetime2 / datetime / smalldatetime; CAST(? AS date) for date; CAST(? AS datetimeoffset(7)) for datetimeoffset; CAST(? AS time(7)) for time; operand unchanged otherwise. ISO strings convert the same way under any language or DATEFORMAT setting. |
| lob_placeholder | EMPTY_BLOB(), EMPTY_CLOB() | 0x for varbinary(max) / image; '' for varchar(max) / text; N'' for nvarchar(max) / ntext |
| row_locator_clauses | tail RETURNING ROWID INTO :n | mid OUTPUT inserted.<key>, tail empty (5c agreed) |
| row_limit_sql | SELECT * FROM (<sql>) WHERE ROWNUM <= n | SELECT TOP (n) * FROM (<sql>) AS dm_t; with a top-level ORDER BY, see 5a |
| count_rows_sql | SELECT COUNT(*) FROM (SELECT 1 FROM (<sql>)) | SELECT COUNT(*) FROM (SELECT 1 AS dm_c FROM (<sql>) AS dm_a) AS dm_b; ORDER BY per 5a |
| now_expr | SYSTIMESTAMP | SYSDATETIME() (server clock; see D7) |
| add_seconds_expr | <base> + NUMTODSINTERVAL(<s>,'SECOND') | DATEADD(second, <s>, <base>) |
| procedure_call_sql | BEGIN proc(:P1, :P2); END; | {CALL proc(?, ?)}; {CALL proc} with no parameters |

### 5a. ORDER BY inside the wrapped query

SQL Server refuses ORDER BY in a derived table unless TOP or OFFSET is also given (error 1033). Oracle accepts it. driver_mssql looks for an ORDER BY at the top level of the user's SQL (outside brackets, strings and comments):

- count_rows_sql appends  OFFSET 0 ROWS to the inner query. Order does not matter for a count.

- row_limit_sql does not wrap the query. It appends  OFFSET 0 ROWS FETCH NEXT n ROWS ONLY instead. This keeps the user's order guaranteed; an outer TOP over an ordered derived table does not guarantee it.

- If the query already ends in OFFSET/FETCH, or begins with TOP, it is wrapped and left as written.

### 5c. Row locator and LOB writes - agreed

SQL Server has no ROWID. INSERT and UPDATE return the row's key with OUTPUT inserted.<key>, and lob_write_by_rowid then writes the LOB with UPDATE <table> SET <col> = ? WHERE <key> = ?, sending the content in chunks (SQL_DATA_AT_EXEC and SQLPutData), so a large file never has to be in memory at once. The key comes from describe_table (primary key first, otherwise a unique index on NOT NULL columns). A table with neither cannot take a LOB write: the request fails with LOB write needs a primary or unique key on <table>. The SQL Server copy of OCI_FIELD_TEST gets an IDENTITY primary key for this.

### 5d. Single-column keys first (D5)

db_rowid_result_t carries one text value per row, which fits a single-column key. Stage 4 supports single-column keys only. A table whose only key has several columns gets the same clear refusal as a table with no key. Composite keys can follow if a real table needs them.

### 5e. Wrapped queries need named, distinct columns (D6)

SQL Server requires every column of a derived table to have a name, and the names to be distinct. Oracle does not. So when the gateway wraps a query for a count or a row limit, SELECT COUNT(*) FROM t (error 8155) or SELECT a.id, b.id ... (error 8156) works on Oracle but fails on SQL Server. Proposal: no SQL rewriting. The gateway returns a clear message: on SQL Server every selected column needs a distinct name - add an alias (AS name). Rewriting the user's select list would mean parsing T-SQL, which is a much larger change for little gain.

## M6. Fetching, metadata and procedures

- Binds. Values arrive as text, and value_expr converts them in SQL, so every parameter is bound as text with SQLBindParameter. NULLs use SQL_NULL_DATA.

- Character data (D4): the DataManager database is created with a UTF-8 collation (Latin1_General_100_CI_AS_SC_UTF8), and text is bound and fetched as UTF-8 (SQL_C_CHAR). The gateway process runs with a UTF-8 locale, which the ODBC driver uses for client-side text. With a non-UTF-8 collation, characters outside that code page would be silently replaced with ? in varchar columns.

- Describe. SQLNumResultCols, SQLDescribeCol and SQLColAttribute(SQL_DESC_TYPE_NAME) fill db_column_meta_t with names and SQL Server type names (nvarchar, datetime2, varbinary ...). A (max) column is recognised by its unlimited length.

- Scalar fetch. Bound array fetch, column-wise: SQL_ATTR_ROW_ARRAY_SIZE = the request's fetch array size, text buffers sized from the column size (capped), and the rows-fetched counter giving the batch length.

- Long columns ((max)). Microsoft's driver reads long data only with SQLGetData, one row at a time, and only for columns after the last bound one. When a result has a (max) column, the cursor binds nothing, fetches one row per call, and reads every column with SQLGetData in order, long ones in chunks. The batch size becomes 1, and <fetch_batch_size> reports the 1 actually used (as it already does for Oracle).

- LOB output. BLOB-class values go to files through the existing Blob_Utils code, and CLOB-class values to text files or inline (text_lobs_inline), with the same lob_output_tag() names and .part writes as Oracle. The tag is taken once per SELECT with a LOB column.

- Type classes. db_type_class.c learns SQL Server's names: char, varchar, nchar, nvarchar, uniqueidentifier, xml (text); int, bigint, smallint, tinyint, bit, decimal, numeric, money, smallmoney, float, real (number); date, time, datetime, datetime2, smalldatetime, datetimeoffset (date and time); varbinary(max) and image (BLOB class); varchar(max), nvarchar(max), text and ntext (CLOB class); binary(n) and varbinary(n) as hex text.

- describe_table. INFORMATION_SCHEMA.COLUMNS joined to sys.columns (for (max), identity and computed columns), and sys.indexes / sys.index_columns for the primary or unique key 5c needs. The owner is the schema name.

### 6c. Procedures - agreed

Calls use {CALL proc(?, ...)} with parameters bound in order: IN as text, OUT and IN OUT as output buffers. With ODBC, OUT parameter values arrive only after every result set has been read (SQLMoreResults returns SQL_NO_DATA). So dml_execute_procedure() reads each result set in full into memory, hands them to the request's CURSOR parameters in order, and only then reads the OUT values. select_open_from_cursor() serves the buffered rows, and cursor_handle_free() frees them. A procedure with more result sets than CURSOR parameters fails clearly; fewer leaves the extra CURSOR parameters empty. A T-SQL RETURN value is not reported.

Cap (D8). Each buffered result set is limited to query_max_record_count rows; rows beyond the cap are read and discarded, and the log says so. This also means SQL Server procedure results honour the limit, which Oracle REF CURSORs do not yet (open item).

## M7. Errors

Every diagnostic record on the failing handle is read with SQLGetDiagRec and reported as SQLSTATE <state> [native <n>]: <text>. Microsoft's bracketed prefix [Microsoft][ODBC Driver 18 for SQL Server][SQL Server] is dropped from the text. Examples: SQLSTATE 23000 [native 2627]: Violation of PRIMARY KEY constraint ..., SQLSTATE 08S01 [native 10054]: .... Stage 2 also checks whether any core code tests Oracle error text (ORA- numbers). If any does, it gets a neutral alternative before driver_mssql relies on it.

## M8. Out of scope

- The DDL module: CREATE/ALTER/DROP requests are refused on SQL Server with a clear message. v1.1: not built - U7 was decided out on 20 Oct; see 9.2.

- Unit_Test_Module's own verification queries, which are Oracle SQL.

- Identical SELECT output on both databases. Dates and numbers come back in each database's own text form. For example, datetime2 is 2026-10-18 09:15:00.0000000.

- Renaming oci_context_t (deferred since M2).

## M9. Build

- New files: src/execute/driver_mssql.c, include/driver_mssql.h; harnesses under src/Drivers/MSSQL/.

- Headers <sql.h>, <sqlext.h> (unixodbc-dev) and <msodbcsql.h> (installed with msodbcsql18 under /opt/microsoft/msodbcsql18/include). Link -lodbc.

- One binary carries both drivers; db_type picks one at run time. The Oracle client libraries stay linked.

- m2_compile_proof.py gains a Part 3: the SQL Server files must compile with every Oracle header blocked, so the two drivers never depend on each other.

## M10. Test database scripts

- Create_MSSQL_Test_Objects.sql (run once with sqlcmd as an administrator, prompting for the password): database DataManager with the UTF-8 collation and READ_COMMITTED_SNAPSHOT ON; login and user DATA_MANAGER with schema DATA_MANAGER as its default; the test tables with the same seed rows as Oracle (OCI_FIELD_TEST with an IDENTITY key, seed rows 4242-4244 with the same CLOB and BLOB values); the security, session, audit and metrics tables, keeping their OCI_ names so core SQL is unchanged; and T-SQL versions of the test procedures.

- Reset_Tester_Objects_mssql.sql: the SQL Server counterpart of Reset_Tester_Objects.sql. Every line reports ok or absent, as now.

- The scripts contain no passwords. The DATA_MANAGER password is passed in as a sqlcmd variable at run time.

# 4. Stages (M11)

Each stage is proposed, agreed, built, and proven before the next one starts. At every stage Oracle must still give 13/13 and 109/109, and the compile proof must PASS.

| Stage | Content | Proof |
| --- | --- | --- |
| 1 | M10 scripts. Database, login, tables, seed rows, procedures, reset script. | Scripts run clean twice; row counts and seed LOB values checked with sqlcmd. |
| 2 | Dispatch and connection: db_type, mssql keys, db_driver_get(), connect, disconnect, pool, session_is_alive, reconnect, health_check, commit, rollback, M7 errors. Check core for Oracle error-text tests. | Driver_MSSQL_Connect_Test and Driver_MSSQL_Pool_Test; gateway starts on SQL Server and answers a health check; Oracle unchanged. |
| 3 | Dialect (all nine hooks), scalar SELECT, describe_table, type classes. | Driver_MSSQL_Dialect_Test (exact SQL text, including 5a); Driver_MSSQL_Select_Test; Driver_MSSQL_Metadata_Test. |
| 4 | DML: dml_execute, OUTPUT row locator, LOB writes (5c, 5d), transactions. | Insert, Update, Delete and Transaction harnesses; LOB content read back byte for byte. |
| 5 | LOB SELECT: (max) columns, SQLGetData, LOB files. | Driver_MSSQL_LOB_Select_Test; Check_LOB_Files.py against SQL Server (30 of 30 right). |
| 6 | Procedures (6c). | Driver_MSSQL_Procedure_Test: IN, OUT, IN OUT, several result sets, cap. |
| 7 | End to end: the HTTP tester against a gateway on SQL Server (D10). | SQL Server fixture set passes; Oracle 109/109. |

# 5. Decisions for agreement

All ten were agreed on 18 Oct as proposed. Where the build differs, Section 9.2 says how and why.

| # | Decision | Proposed |
| --- | --- | --- |
| D1 | Config key names and defaults (M3) | As listed in M3; the password held the same way as the Oracle one. |
| D2 | Retry on commit failure (M4) | Never retryable: deadlock 1205 and connection loss 08S01 fail at once. |
| D3 | Read consistency (M4) | READ_COMMITTED_SNAPSHOT ON on DataManager. |
| D4 | Character data (M6) | UTF-8 collation Latin1_General_100_CI_AS_SC_UTF8; UTF-8 binds and fetches. |
| D5 | Keys for LOB writes (5d) | Single-column primary or unique keys only, for now. |
| D6 | Unnamed or duplicate columns in wrapped queries (5e) | Clear error asking for an alias; no SQL rewriting. |
| D7 | Server clock (M5 now_expr) | Check SELECT SYSDATETIMEOFFSET() in the container. If it shows +00:00 while the gateway runs on Irish time, re-create the container with -e TZ=Europe/Dublin (the volume keeps the data), so stored times read the same as on Oracle. |
| D8 | Procedure result-set cap (6c) | query_max_record_count rows per result set; extra rows discarded and logged. |
| D9 | Harnesses | New Driver_MSSQL_*_Test.c files and Get_Test_Results_mssql.sh; the Oracle 13 are unchanged. |
| D10 | HTTP tester on SQL Server (stage 7) | A separate fixture folder and baselines for SQL Server, starting from the fixtures whose SQL is plain enough to run on both; Oracle-only fixtures (PL/SQL, DUAL, ROWNUM, DDL) stay Oracle-only. Its own run plan. The fixture list is settled at stage 7. |

# 6. Risks

| Risk | Handling |
| --- | --- |
| OUTPUT without INTO fails on a table that has enabled triggers (error 334). | The test tables have no triggers. If a real table does, OUTPUT ... INTO a table variable is the fix; logged as a follow-up, not built now. |
| Long data reads one row at a time (batch size 1), which is slower for big LOB result sets. | Same as Oracle's LOB path in practice. The batch size actually used is reported, so the cost is visible. |
| Buffered procedure results use memory. | Capped by D8. |
| Ubuntu 25.04 is past end of life, and the ODBC driver came from Microsoft's 24.04 feed. | Works today. Move the laptop to 26.04 LTS when convenient and re-check the driver install. |
| Behaviour that differs from Oracle, such as empty string versus NULL (Oracle stores '' as NULL; SQL Server keeps ''). | Accepted as database behaviour; noted where a SQL Server baseline differs from Oracle's. |

# 7. Definition of done

- Stages 1-7 closed, each with its proof.

- Oracle: Get_Test_Results.sh 13/13 and tester 109/109 after the last stage.

- SQL Server: all Driver_MSSQL_* harnesses PASS within the leak baseline; Check_LOB_Files.py 30 of 30; the SQL Server fixture set passes.

- DoD_Greps.sh (Greps 1-2) reports nothing; Grep 3, m2_compile_proof.py, reports PASS for all three parts.

- No password in any config file, script or project document; the gateway connects as DATA_MANAGER.

# 8. Proof method

Unchanged from the Oracle work. Build; Get_Test_Results.sh 13/13 (plus the SQL Server harnesses from stage 2); reset; HTTP tester run; review the diffs; promote reviewed .current files. Each stage arrives as an apply script (dry run by default, --apply, .bak backups, refuses to run twice, every edit matches exactly once) or as whole new files.

# 9. As built (Stages 1-7, 18-24 October)

This section records what was actually built. Where it differs from Sections 3-8, this section is the one that holds. Each stage was proposed in points, agreed, built against a stand-in ODBC library first, and then proven live. The status notes in the project (claude/driver_mssql_stage*_status_*.md) have the details.

## 9.1 Stages

| Stage | Closed | Built | Live proof |
| --- | --- | --- | --- |
| 1 | 18 Oct | Create_MSSQL_Test_Objects.sql (as sa), Reset_Tester_Objects_mssql.sql and Check_MSSQL_Test_Objects.sql (as DATA_MANAGER), plus the local-only MSSQL_Security_Seed.sql | Build clean; reset clean twice; a second build refused; checks 40/40 (42/42 after the V1 grant) |
| 2 | 19 Oct | db_type dispatch, connection keys, MSSQL_Pool.c, commit and rollback, M7 errors | Connect 7/7, Pool 8/8; gateway starts on SQL Server |
| 3 | 20 Oct | Dialect (mssql_dialect.c), scalar SELECT (mssql_select.c), describe_table (mssql_metadata.c), type classes | Dialect, Select, Metadata harnesses; Check 42/42 |
| 4 | 20 Oct | DML (mssql_dml.c), the table_key hook, OUTPUT row locator, LOB writes, text LOBs bound in the statement (lob_text_bind.c) | 8 harnesses PASS; CREATE_SESSION through the gateway |
| 5 | 21 Oct | LOB SELECT (long columns via SQLGetData), statement text as UTF-16 (mssql_text.c) | 9 harnesses PASS; the tester through the SQL Server gateway logs in (all 10 Authenticate rounds) |
| 6 | 22 Oct | Procedures (mssql_proc.c): buffered result sets as CURSOR parameters, OUT values after the results, autocommit for calls with no gateway transaction | 10 harnesses PASS, Procedure 20/20; Procedure Rounds 1 and 4 pass through the gateway |
| 7 | 24 Oct (see 9.7) | Testers/Run_mssql.sh, mssql_excluded.txt, baseline_mssql (87 Oracle baselines copied, 6 SQL Server baselines reviewed), Threading=1 | Run_mssql.sh twice in a row: 93 run, 86 pass, 7 expected differences, 0 fail; Oracle 109/109 twice; SQL Server harnesses 10/10 under Threading=1 |

At every stage Oracle kept 13/13 harnesses and 109/109 in the tester, and m2_compile_proof.py passed (74 core files with every Oracle header blocked, plus 19 Oracle-side files, at Stage 6).

## 9.2 Where the build differs from this proposal

| Point | Proposed | As built, and why |
| --- | --- | --- |
| M3 / D1 keys | mssql_server, mssql_port, mssql_database, mssql_user, mssql_password, ... | The existing dbname, username and password keys are reused, plus mssql_server, mssql_port, mssql_trust_server_certificate and mssql_login_timeout. Bootstrap's metrics-pool override then works unchanged. Props/config_mssql.ini holds the password and stays local, out of the project and git. |
| M5 add_seconds_expr | DATEADD(second, <s>, <base>) | DATEADD(second, CAST(<s> AS int), <base>). DATEADD refuses a bigint (error 8116), and OCI_SESSION.TTL_SECONDS is bigint. |
| M5 value_expr, lob_placeholder | Binary values not covered; 0x, '' and N'' placeholders | Binary values are sent as CONVERT(varbinary(max), ?, 2). lob_placeholder gives 0x only for varbinary(max) and image; text LOBs need no placeholder (next row). |
| 5c row locator | Key from describe_table | A new driver hook, table_key (U1), returns the key: the primary key, or a unique unfiltered index on one NOT NULL column, cached per table. Oracle returns none (ROWID). The key text must fit in 23 characters (ROWID_BUF_SIZE), so a uniqueidentifier key is refused. A table with no single-column key gets no OUTPUT clause and cannot take a LOB write. |
| 5c LOB writes | All LOBs written after the row by lob_write_by_rowid | Only varbinary(max) and image are written after the row. varchar(max), nvarchar(max), text, ntext and xml are bound in the statement itself (U6, option B), so AUDIT_TRAIL never needs an UPDATE and stays write-once by DENY. Text over 4000 UTF-16 units is bound as SQL_WVARCHAR with SQL_SS_LENGTH_UNLIMITED (Stage 4 Fix 1); the long-data type was sent as the legacy ntext. |
| M6 character data | UTF-8 binds and fetches | As proposed for values. Statement text itself goes as UTF-16, because the narrow ODBC calls garbled non-ASCII literals (Stage 5 Fix 1). SELECT binds over 4000 UTF-16 units are bound as nvarchar(max) (W6). |
| M6 long columns | Batch size becomes 1 | Rows are read one at a time with SQLGetData, but the batch stays at the requested size, so <fetch_batch_size> reports 5 where Oracle reports 1 (a documented baseline difference). CLR types are refused, named by the driver as udt. |
| 6c extra result sets | More result sets than CURSOR parameters fails | The extra result sets are read and discarded, with a WARN in the log. |
| 6c / D8 cap | Rows beyond query_max_record_count discarded | A result set with more rows than query_max_record_count fails the call. A SELECT is truncated instead. |
| 6c / M4 procedures and transactions | Not covered | See 9.3. With no gateway transaction, the call runs in autocommit and manual-commit is restored afterwards (Stage 6 Fix 2). |
| M8 DDL | Refused on SQL Server with a clear message | Not refused (U7 decided out, 20 Oct). The core DDL modules build Oracle DDL text, so DDL requests fail at the database on SQL Server. The DDL and security-admin fixtures are left out of the SQL Server tester run (9.5). |
| M9 names | Driver_MSSQL_*_Test.c | src/Drivers/MSSQL/MSSQL_Driver_*_Test.c (so Get_Test_Results.sh's Oracle glob does not pick them up), built by MSSQL_Server/Build_MSSQL_Harnesses.sh: Connect, Pool, Dialect, Select, Metadata, DML, LOB_Write, Transaction, LOB_Select, Procedure. |
| M10 procedures | T-SQL versions in Create_MSSQL_Test_Objects.sql | The 8 shared procedures are there (S9). The six MS_TEST_ procedures that only the Procedure harness uses are in Create_Test_Procedures_mssql.sql (run as sa; safe to re-run). The header of Create_MSSQL_Test_Objects.sql gives the order. |
| D10 tester | A separate fixture folder | The same fixture folders, minus 16 fixtures listed with reasons in Testers/mssql_excluded.txt, and a separate baseline set, Testers/baseline_mssql. See 9.5. |

## 9.3 Rule for procedures that commit (Terry, 22 Oct)

A procedure that commits or rolls back by itself is called with <transaction required="0">, the same as DDL. The gateway cannot see inside a procedure, so it cannot enforce this; Data_Manager_Request_Definitions v1.6 states it under EXECUTE_PROCEDURE.

- Why it matters on SQL Server. With autocommit off, any statement opens a transaction, including the statement that calls the procedure. A procedure that commits inside that transaction ends with error 266, and by then SQL Server has already committed the caller's work.

- With no gateway transaction, the driver rolls back the connection's open read transaction, runs the call in autocommit, and restores manual-commit afterwards, success or failure. A failed restore fails the call.

- Inside a gateway transaction nothing is changed: a self-committing procedure fails with 266.

- A procedure that does not commit can still run inside a gateway transaction. Called with required="0", its work is committed statement by statement on SQL Server; Oracle would leave it pending.

## 9.4 Deployment prerequisites (SQL Server)

| Prerequisite | Why |
| --- | --- |
| Database collation Latin1_General_100_CI_AS_SC_UTF8, READ_COMMITTED_SNAPSHOT ON (D3, D4) | UTF-8 text without loss; readers do not wait for writers. |
| Login and user DATA_MANAGER; schema DATA_MANAGER owned by dbo; SELECT, INSERT, UPDATE, DELETE and EXECUTE on the schema | The gateway never connects as sa. AUDIT_TRAIL is write-once by DENY UPDATE, DELETE. |
| GRANT VIEW DEFINITION ON SCHEMA::DATA_MANAGER TO DATA_MANAGER | Without it, SQL Server hides column defaults, and describe_table reports them empty (Level 2 then demands values that have defaults). In Create_MSSQL_Test_Objects.sql (S3) and checked by Check_MSSQL_Test_Objects.sql. |
| /etc/odbcinst.ini, entry [ODBC Driver 18 for SQL Server]: Threading=1 | unixODBC's default (3, when the line is absent) serialises every ODBC call in the process across all pooled connections. Level 1 serialises per statement, and connections run in parallel. Set 23 Oct; proven by the Pool harness (8 threads) and the tester. Needs root, and a gateway restart. |
| TrustServerCertificate=yes only for the self-signed test container | Driver 18 encrypts by default. A real server should present a trusted certificate. |
| Self-committing procedures called with required="0" | See 9.3. |

## 9.5 The tester on SQL Server (Stage 7)

- Testers/Run_mssql.sh asks once for the DATA_MANAGER password (not echoed; passed to sqlcmd through SQLCMDPASSWORD, never -P). It then: resets the test objects and checks that all four ok lines were printed (if not, the tester is not run); copies the *.xml and *.json fixtures, minus the exclusions; filters the run plan; runs the tester against ./baseline_mssql; and resets again, so the SQL Server harnesses always find the seed rows.

- Excluded, 16 fixtures: the DDL and security-admin rounds that send Oracle syntax (CreateTable_1, CreateView_1, DropTable_1, DropTable_4_DESTRUCTIVE, CreateProcedure_1, DDL_Sequence_1, CreateUser_1, Grant_1, xml and json). The error-path DDL and security rounds still run, because they fail in Level 2, before the database. 93 fixtures run.

- Baselines: 87 are the Oracle baselines, copied unchanged. 6 are SQL Server's own, each reviewed against Oracle on 23 Oct and recorded in baseline_mssql/README.txt:

| Fixture | Allowed difference from Oracle |
| --- | --- |
| select_integration_tests (xml, json) | Alias case Second_Blob (SQL Server keeps the case as written); seed text Adams pizza; fetch_batch_size 5 |
| Unit_Test_Procedure_Round_2 (xml, json) | DATE_COL reported as TIMESTAMP / 2030-01-01 00:00:00 (datetime2) |
| Verify_Round_5_Clob.xml | fetch_batch_size 5 vs 1 |
| Request_Test_Select_2.json | Table definition (FIELD_TEST_ID on SQL Server only; ROWID_COL, UROWID_COL on Oracle only); float and date/time types reported with their type and plain or ISO text, where Oracle reports UNKNOWN or NLS text. Same row, same values. |

- Fixture change (Z4): Verify_Round_5_Clob.xml gained ORDER BY NUMBER_COL (new MD5 2f3822848e8a3cebd5f08bb9792cc61b). Without it the row order was not guaranteed, which is the likely cause of its occasional Oracle failures. Both baselines were regenerated and reviewed.

## 9.6 Known differences from Oracle, and open items

Differences accepted as database behaviour:

- With autocommit off, a SQL Server SELECT opens a transaction. A read-only request leaves it open on the worker connection until something ends it. Under read-committed snapshot it takes no locks, but SQL Server keeps row versions in tempdb for it (Z7, documented; to revisit before the gateway serves SQL Server for real: a core rollback after every request with no managed transaction, or plain reads in autocommit).

- Dates come back in each database's own form: datetime2 as TIMESTAMP with ISO text.

- Unquoted aliases keep their case on SQL Server.

- <fetch_batch_size> with a CLOB column: 5 on SQL Server, 1 on Oracle.

- A self-committing procedure inside a gateway transaction: error 266 on SQL Server; Oracle commits silently (9.3).

Open items (recorded, not changed):

- Z7, above.

- SQLGetDiagRec text is read narrow, so non-ASCII characters in server messages may be garbled.

- OUTPUT without INTO fails on a table with enabled triggers (error 334); composite keys for LOB writes (D5). Neither is needed by any current table.

- D7: the container clock was UTC (SYSDATETIMEOFFSET +00:00) when checked on 18 Oct; re-create mssql2022 with -e TZ=Europe/Dublin if not yet done.

- Oracle side, found along the way: oracle_fetch_blob_field() does not check write_blob_to_file()'s result, and the Oracle driver reports UNKNOWN for 9 types (BINARY_FLOAT/DOUBLE, TIMESTAMP TZ/LTZ, the two intervals, RAW, ROWID, UROWID).

## 9.7 Definition of done - status

| Item (Section 7) | Status |
| --- | --- |
| 1. Stages 1-7 closed | 1-6 closed. 7: proof in progress - remaining steps are the Oracle harnesses, m2_compile_proof.py and the gateway smoke test. |
| 2. Oracle 13/13 and 109/109 | 109/109 twice on 24 Oct; 13/13 at Stage 6, to repeat for Stage 7. |
| 3. SQL Server harnesses, Check_LOB_Files.py, fixture set | Harnesses 10/10, no leaks (23 Oct, Threading=1). Fixture set: 0 fail, twice (24 Oct). Check_LOB_Files.py has not yet been run against SQL Server. |
| 4. DoD greps and compile proof | m2_compile_proof.py PASS at every stage so far; DoD_Greps.sh to run at close. |
| 5. No passwords; DATA_MANAGER login | Met. Passwords are typed at a prompt (read -s, sqlcmd's own prompt or SQLCMDPASSWORD); config_mssql.ini and MSSQL_Security_Seed.sql stay local. |